## Property_Survey
SITE ACQUISITION
DUE DILIGENCE
In order to become a “Kentucky Development Ready Site” the following checklist of potential needs for the primary areas of survey and engineering will need to be addressed. The checklist is generally broken into three steps for each category recognizing that variances will occur for individual circumstances.
PROPERTY/SURVEY | UTILITIES ACCESS | GEOTECHNICAL DETERMINATIONS | TRANSPORTATION ROADWAY/RAIL | SITE CONSTRUCABILITY, LAYOT & COSTS | ENVIRONMENTAL STEPS
PROPERTY/SURVEY CHECKLIST
STEP 1: Define existing owners, basic boundaries, and desired total property boundary
GOAL: Clarify that there is a path to ownership, collect basic property information.
COMPLETED | NOT COMPLETE | MAJOR ACTION ITEMS |  |  |  | NOTES
TRUE | FALSE | Boundary research: deed plots, plat plots Understand easement/rights of way/ encumbrances
FALSE | FALSE | Obtain LiDAR and other available maps
TRUE | FALSE | Narrative describing topography of the property
TRUE | FALSE | Narrative describing the plan for handling future costs, cost estimate for planned actions, schedule, and documentation of the next steps needed for the property
DELIVERABLE(S): Map of the property depicting known items discovered/ known. Determination of next steps that will be taken once a potential industry declares interest in the site.
STEP 2: Boundary Survey
GOAL: Interest in the property is increasing, site may be shortlisted, and further definition of the site boundary is warranted. Additionally, any encumbrances need to be defined as well.
COMPLETED | NOT COMPLETE | MAJOR ACTION ITEMS |  |  |  | NOTES
TRUE | FALSE | Boundary Confirmation through standard survey practices
TRUE | FALSE | Additional encumbrance research
TRUE | FALSE | Narrative describing topography of the property
TRUE | FALSE | Without completing a full title search, Identify leasehold or other rights of possession, including without limitation all rights to access or use the surface of the property to access any oil, gas, or other minerals or substances
TRUE | FALSE | Identify Ingress/egress or required easements (indicating there are no known impediments to right-of-way acquisition for incoming roads and utilities).
FALSE | FALSE | Describe the clear path to elimination of all encumbrances with definition of cost and schedule
FALSE | FALSE | Document the plan for finalizing acquisition of the property along with costs, responsibility for those costs and timeline
DELIVERABLE(S): Map of the property depicting known items discovered/ known. Determination of next steps that will be taken once a potential industry declares interest in the site.
STEP 3: Alta, title
GOAL: Clear ownership concerns. Prepare for full property acquisition
COMPLETED | NOT COMPLETE | MAJOR ACTION ITEMS |  |  |  | NOTES
TRUE | FALSE | Final determination of Encumbrances’: IE easements, access rights, rights of way, exceptions, subterranean rights, drilling rights, etc.
TRUE | FALSE | Topography update via field shot verification and/or LiDAR flight
TRUE | FALSE | Up to date Aerial Photography
TRUE | FALSE | ALTA Survey
TRUE | FALSE | Title Determination
FALSE | TRUE | Required Buffer zone, if any, is established/preserved if site adjacent to residential or commercial area
FALSE | FALSE | Written Statement - No parties in possession or with leasehold or other rights of possession, including without limitation all rights to access or use the surface of the property to access any oil, gas, or other minerals or substances
TRUE | FALSE | Ingress/egress or required easements (indicating there are no known impediments to right-of-way acquisition for incoming roads and utilities)
TRUE | FALSE | Clear path to elimination of all encumbrances with definition of cost and schedule
DELIVERABLE(S): Final deliverable is an ALTA survey and Title determination. Documentation of the process of removal of all monetary encumbrances and any matters of record (or shown on a current survey) which would impair the development of the property for its intended use.
PROPERTY/SURVEY | UTILITIES ACCESS | GEOTECHNICAL DETERMINATIONS | TRANSPORTATION ROADWAY/RAIL | SITE CONSTRUCABILITY, LAYOT & COSTS | ENVIRONMENTAL STEPS
UTILITY ACCESS CHECKLIST
STEP 1: Determine existing availability and current capacity to serve.
GOAL: Understanding available utility services, limitations and capabilities, and costs to achieve improved serviceability.
COMPLETED | NOT COMPLETE | MAJOR ACTION ITEMS |  |  |  | NOTES
TRUE | FALSE | Up to date map of current utilities in place or best available desktop data
TRUE | FALSE | Map of any proposed utilities with full description of owner, schedule, funding sources and proposed utility capacity
TRUE | FALSE | Documentation of communication efforts, utility owners/contacts, and necessary future actions needed to achieve “Kentucky Ready Site”
DELIVERABLE(S): Utility map (electric, gas, telecommunications, sewers, water, stormwater).
STEP 2: Further development of potential preliminary utility improvements
GOAL: Individual properties and industries will have specific requirements for service. This step will clearly identify those improvements, locations, impacts, costs, and schedule.
COMPLETED | NOT COMPLETE | MAJOR ACTION ITEMS |  |  |  | NOTES
TRUE | FALSE | Documentation of coordination with each utility
FALSE | FALSE | Definition of service levels necessary for desired development types. These levels of service needs will be assumed in lieu of the acquisition of specific prospects
TRUE | FALSE | With the help of the utility, develop a map of proposed utilities specific to the site along with a budgetary estimate and schedule for the improvements understanding the utility’s role in the expenditure
TRUE | FALSE | Documentation of communications with authorities having jurisdiction including confirmation of the approval processes and timelines
DELIVERABLE(S): Map of existing utilities and proposed utilities displaying preliminary planned improvements, narrative describing who is responsible for costs, cost estimate, schedule, and confirmation of approvability.
STEP 3: Industry specific development of utility needs and necessary approvals
GOAL: Clearly identify proposed improvements for specific proposed industries including improvement locations, impacts, costs, and schedule.
COMPLETED | NOT COMPLETE | MAJOR ACTION ITEMS |  |  |  | NOTES
TRUE | FALSE | Definition and documentation of service levels necessary for industry considering the site dynamics
TRUE | FALSE | Map of proposed utilities edited to handle the specific needs for the prospective industry
TRUE | FALSE | Updated Documentation of authorities having jurisdiction approval processes, cost, schedule (timeline) and Key Individuals/Organizations involved in the process
FALSE | FALSE | “Will serve letter” from each utility guaranteeing service to the property
FALSE | FALSE | Situationally specific documentation of participants in costs for the proposed improvements
TRUE | FALSE | Documentation of communication with utility owner and regulators
DELIVERABLE(S): Final deliverable is an ALTA survey and Title determination. Documentation of the process of removal of all monetary encumbrances and any matters of record (or shown on a current survey) which would impair the development of the property for its intended use.
PROPERTY/SURVEY | UTILITIES ACCESS | GEOTECHNICAL DETERMINATIONS | TRANSPORTATION ROADWAY/RAIL | SITE CONSTRUCABILITY, LAYOT & COSTS | ENVIRONMENTAL STEPS
GEOTECHNICAL DETERMINATION CHECKLIST
STEP 1: Document a representative soil and rock characterization for the property.
GOAL: Understand prospective construction impacts and requirements.
COMPLETED | NOT COMPLETE | MAJOR ACTION ITEMS |  |  |  | NOTES
TRUE | FALSE | Complete a desktop review of available soils information gathering any data from nearby sites or past work on the site
TRUE | FALSE | Map of findings and narrative of known/ expected soils and rock information
TRUE | FALSE | Projection of next steps, time frame, responsibility, and costs
DELIVERABLE(S): Map of known information shown on desired site boundary.
STEP 2: Document representative soil and rock characterization for the property.
GOAL: Further define prospective construction impacts and requirements.
COMPLETED | NOT COMPLETE | MAJOR ACTION ITEMS |  |  |  | NOTES
TRUE | FALSE | Utilize the desktop review and desired industry type to determine a minimum amount of field geotechnical exploration that will further clarity the expected soil and rock for the site
TRUE | FALSE | Complete initial soil borings necessary to allow a geotechnical engineer to document their expectation of soils on the property
TRUE | FALSE | Map of findings and initial rock surface depths
FALSE | FALSE | Projection of next steps, time frame and costs
DELIVERABLE(S): Boring location map, boring logs, report documenting findings and future actions and costs.
STEP 3: Complete Borings specific to planned improvements associated with a specific user/entity.
GOAL: Define soils information necessary to accurately complete earthwork and more specifically identify available resident soil bearing capacities, and rock strength.
COMPLETED | NOT COMPLETE | MAJOR ACTION ITEMS |  |  |  | NOTES
TRUE | FALSE | Complete industry specific additional soil borings necessary to allow a geotechnical engineer to document design requirements for improvements
FALSE | FALSE | Document capabilities, needs, and opportunities
DELIVERABLE(S):
PROPERTY/SURVEY | UTILITIES ACCESS | GEOTECHNICAL DETERMINATIONS | TRANSPORTATION ROADWAY/RAIL | SITE CONSTRUCABILITY, LAYOT & COSTS | ENVIRONMENTAL STEPS
GEOTECHNICAL DETERMINATION CHECKLIST
STEP 1: Collect existing data, documents, existing proposed improvement projects and studies, review existing capacities, and meet with KYTC and Rail leadership.
GOAL: Document capabilities, needs, and opportunities.
COMPLETED | NOT COMPLETE | MAJOR ACTION ITEMS |  |  |  | NOTES
TRUE | FALSE | Review levels of service available and document potential challenges or advantages for the site
TRUE | FALSE | Create Maps of findings
TRUE | FALSE | Document interactions with KYTC and Rail companies, work to initiate beneficial improvements
FALSE | FALSE | Documentation of design and approval processes, complete initial infrastructure investment projection, document timeline required, and Key individuals/Organizations involved in the process
DELIVERABLE(S): Existing infrastructure and proposed infrastructure mapping, cost and schedule
STEP 2: Interest in the site is increasing and requires the collection additional data, documents, and any updated proposed improvement projects and studies, review any new capacity information, and advance coordination with KYTC and Rail leadership.
GOAL: Further document capabilities, needs, and opportunities.
COMPLETED | NOT COMPLETE | MAJOR ACTION ITEMS |  |  |  | NOTES
FALSE | FALSE | Review levels of service available and likely needed for the new industry, complete initial traffic analysis using available data
FALSE | FALSE | Create Maps of findings share with all parties
FALSE | FALSE | Document interactions with KYTC and Rail companies, work to initiate beneficial improvements
FALSE | FALSE | Documentation of design and approval processes, complete initial infrastructure investment projection, document timeline required and Key Individuals/Organizations involved in the process
DELIVERABLE(S): Existing infrastructure and proposed infrastructure mapping, cost and schedule.
STEP 3: Site is shortlisted, and specific costs need to be determined in order to land new industry. Collect new / current traffic data, utilize specific projected loadings from industries to project and coordinate targeted improvements.
GOAL: Create improvements specific to community and Industry needs.
COMPLETED | NOT COMPLETE | MAJOR ACTION ITEMS |  |  |  | NOTES
FALSE | FALSE | Better define the existing traffic loadings
FALSE | FALSE | Refine projected improvements considering specific loading and use data from the industry identified
FALSE | FALSE | Document interactions with KYTC and Rail companies, refined identification beneficial improvements
FALSE | FALSE | Documentation of design and approval processes, complete initial infrastructure investment projection, document timeline required, and Key Individuals/Organizations involved in the process
DELIVERABLE(S): Mapping of existing infrastructure and refined proposed infrastructure mapping, cost and schedule, and traffic studies.
PROPERTY/SURVEY | UTILITIES ACCESS | GEOTECHNICAL DETERMINATIONS | TRANSPORTATION ROADWAY/RAIL | SITE CONSTRUCABILITY, LAYOT & COSTS | ENVIRONMENTAL STEPS
SITE CONSTRUCTABILITY, LAYOUT & COST CHECKLIST
STEP 1: Identify types and sizes of industry that are likely to utilize the subject property.
GOAL: Utilize survey, utility, and geotechnical information to document the available development size, layout options, and utility service needs on site.
COMPLETED | NOT COMPLETE | MAJOR ACTION ITEMS |  |  |  | NOTES
FALSE | FALSE | Collect available mapping (utilize statewide LiDAR or complete LiDAR collection)
FALSE | FALSE | Utilize any Zoning, and site-specific development requirements, set-backs, buffers, etc. to refine the proposed development. Document requirements and any written confirmation from local authorities regarding the development of the site
FALSE | FALSE | Utilize Survey, Geotechnical, and Environmental Data to map out restrictions, rock depth, and any obstacles to development
FALSE | FALSE | Identify 2D layout alternatives for potential industries. 3D can be developed to further generate interest, but is not necessary
FALSE | FALSE | Complete mapping of data created including proposed layouts integrated with the findings from other disciplines
FALSE | FALSE | Documentation of water quality and quantity requirements, approvals, approval processes, cost, schedule, and Key Individuals/Organizations involved in the process
DELIVERABLE(S): Exhibits of existing conditions, layout alternatives, proposed layouts, costs, and narrative of the path forward.
STEP 2: Site is generating interest and specific industry types are expected. Identify specific development information to further define pad ready needs, costs, schedules, etc.
GOAL: Further develop layout options, costs, and utility service needs on site.
COMPLETED | NOT COMPLETE | MAJOR ACTION ITEMS |  |  |  | NOTES
FALSE | FALSE | Collect any new mapping, potentially fly new LiDAR if mapping is not representative of the current conditions
TRUE | FALSE | Utilize new Survey, Geotechnical, and Environmental Data to map out restrictions, rock depth, and any obstacles to development
FALSE | FALSE | Further develop specific alternatives for known industries of interest
FALSE | FALSE | Complete mapping of data created including proposed layouts, grading, utilities and site roadways
FALSE | FALSE | Add to the documentation of water quality and quantity needs, approvals, approval processes, cost, schedule, and Key Individuals/Organizations involved in the process
DELIVERABLE(S): Revised exhibits of existing conditions, alternatives, proposed layouts, costs, and narrative of the path forward.
STEP 3: A specific industry has shortlisted the property or is considering final selection, final determination of site engineering and construction needs, schedule, and cost are required.
GOAL: Utilizing a surveyed boundary for the property, known geotechnical data, grading efforts, and utilities coordination efforts, document the pad ready costs to deliver the property to the industry as negotiated.
COMPLETED | NOT COMPLETE | MAJOR ACTION ITEMS |  |  |  | NOTES
FALSE | FALSE | Collect industry specific layout of company specific infrastructure or an example of similar needs and apply it to the specific site
FALSE | FALSE | Document zoning requirements, and site-specific development requirements, set-backs, buffers, etc. and apply to identified industrial user
FALSE | FALSE | Utilize any new Survey, Geotechnical, and Environmental Data to update and map out restrictions, rock depth, and any obstacles to development
FALSE | FALSE | Refine layout based on local authority and proposed industry feedback and complete refined analysis of cut and fill, and site infrastructure improvements necessary to be pad ready
FALSE | FALSE | Complete mapping of data created including proposed layouts, grading, utilities and site roadways
FALSE | FALSE | Documentation of water quality and quantity needs, approvals, approval processes, cost, schedule and Key Individuals/Organizations involved in the process
DELIVERABLE(S): Engineering Reports, mass cut and fill, grading, clearing, demolition, utility relocations, on site roadway improvements, disturbed limits, initial review of stormwater requirements, costs, schedule and regulatory approval needs.
PROPERTY/SURVEY | UTILITIES ACCESS | GEOTECHNICAL DETERMINATIONS | TRANSPORTATION ROADWAY/RAIL | SITE CONSTRUCABILITY, LAYOT & COSTS | ENVIRONMENTAL STEPS
ENVIRONMENTAL STEPS CHECKLIST
STEP 1: Overview
GOAL: Identify major issues.
COMPLETED | NOT COMPLETE | MAJOR ACTION ITEMS |  |  |  | NOTES
TRUE | FALSE | OFFICE OF STATE ARCHAEOLOGY (OSA) SITE CHECK: This involves researching past archaeological research and findings in the vicinity of the project site to determine if there are any known archaeological sites or the likelihood of archaeological resources within the project area. This is required before the Phase 1 field work (Step 2) can occur.
TRUE | FALSE | KENTUCKY HERITAGE COUNCIL (KHC) SITE CHECK: This step involves identifying previously recorded historic resources within the assumed Area of Potential Effect (APE) of the project site, helping to assess potential impacts on historic sites.
TRUE | FALSE | HISTORIAN SITE VISIT: This involves a visit by a SHPO-qualified historian to the project area to verify the results of the KHC Site Check and identify additional potentially eligible historic resources within or near the project APE.
TRUE | FALSE | KY DIVISION OF WATER (KDOW) MAP PORTAL SEARCH: This involves searching KDOW maps to identify any special use waters, such as “Section 404” waters, which would require permits for impacts to streams.
TRUE | FALSE | NATIONAL WETLANDS INVENTORY (NWI) SITE CHECK: This involves checking the NWI to identify potential wetland areas within or near the project site, which may require preservation, permitting, or mitigation. ENDANGERED SPECIES IPAC SITE CHECK: This step involves searching the USFWS database to identify any protected species within the County and potential habitat within the project area, ensuring compliance with endangered species regulations.
FALSE | FALSE | USEPA ENVIRONMENTAL JUSTICE (EJ) COMMUNITY TOOL WEBSITE: This involves using the EPA’s EJ Community Tool website to identify areas of low- income or minority populations that could be impacted or benefit from the project, helping to assess environmental justice considerations.
FALSE | FALSE | HAZMAT DATABASE SEARCH: This step involves searching hazmat databases to identify any known past spills, permits uses of hazardous material, or other recognized environmental concerns (RECs) within or near the project site.
FALSE | FALSE | HAZMAT FIELD VISIT: This involves a visit to the project site by hazmat specialists to verify the results of the Hazmat database search and identify any potential RECs not recorded in the databases.
DELIVERABLE(S): Overview map and document.
STEP 2: ENVIRONMENTAL REPORT APPROVALS
GOAL: AGENCY APPROVALS OF EXISTING CONDITIONS AND IMPACTS.
COMPLETED | NOT COMPLETE | MAJOR ACTION ITEMS |  |  |  | NOTES
TRUE | FALSE | PHASE 1 ARCHAEOLOGY SURVEY: This entails conducting survey test probes (STPs) to locate potentially eligible sites. The Phase 1 report will make recommendations regarding eligibility, and must be accepted by the Kentucky State Historic Preservation Officer (SHPO). Should potentially eligible sites be discovered, an Archaeology Management Plan accepted by the KY SHPO is required in Step 1.
TRUE | FALSE | HISTORIC ELIGIBILITY REPORT: First, approval of the Area of Potential Effect (APE) by the KY SHPO’s office is necessary. Then a report, adhering to SHPO’s standards, will identify eligible sites and propose recommendations regarding effects. Additionally, Survey Forms for sites over 50 years old must be submitted to the SHPO’s office for acceptance.
TRUE | FALSE | WATERS OF THE UNITED STATES (WOTUS) PRELIMINARY JURISDICTIONAL DETERMINATIONS (PJD): This entails Identification of streams and wetlands by an ecologists, and coordinated with the US Army Corps of Engineers (USACE) of a Preliminary Jurisdiction Determination (PJC) to secure an Accepted JDs (AJD) for the USACE. Determination of jurisdictional and non-jurisdictional streams and wetlands alike, per the latest USACE policy, will inform the required Fee In Lieu Of (FILO) payment or other mitigation options.
TRUE | FALSE | BIOLOGICAL ASSESSMENT (BA), PER SECTION 7 OF THE ENDANGERED SPECIES ACT (ESA): This involves addressing each listed species for the county, assessing potential impacts on species or habitat, and proposing mitigation measures, including payments to the Imperiled Bat Conservation Fund (IBCF). Approval from the US Fish and Wildlife Service (USFWS) is required, and in cases of adverse effects, formal consultation with the Lead Federal Agency and then issuance of a Biological Opinion may occur, a process that typically takes about six months.
FALSE | FALSE | PHASE 1 HAZMAT DUE DILIGENCE REPORT: Efforts to identify and assess areas with Recognized Environmental Concerns (RECs) are necessary prior to any property ownership transfer. This report helps identify risks related to hazardous materials and ensures proper management and mitigation strategies, including avoidance, are in place.
DELIVERABLE(S): Various baseline reports and resource agency approvals necessary for the permit application.
STEP 3: Mitigation & Permits
GOAL: Satisfy all applicable environmental laws.
COMPLETED | NOT COMPLETE | MAJOR ACTION ITEMS |  |  |  | NOTES
FALSE | FALSE | KDOW AND/OR USACE PERMIT APPLICATIONS AND SUBMITTALS: The USACE application must include approvals from the SHPO and the USFWS. The approval process includes a public notification period that can take over a month to complete.
FALSE | FALSE | MITIGATION FOR ELIGIBLE ARCHAEOLOGY SITES: If eligible Archaeology Sites are impacted, completion of Mitigation Effort (e.g., Phase II or Phase III work) or a commitment to avoid the site entirely is required.
FALSE | FALSE | MITIGATION FOR ELIGIBLE HISTORIC SITES WITH ADVERSE EFFECTS: Should eligible Historic Sites receive a finding of Adverse Effect (AE) from the SHPO and Lead Federal Agency, engagement opportunities for Consulting Parties (CPs) such as local officials and landowners must be provided. The Advisory Council on Historic Preservation (ACHP) also needs to be notified. With input from the CPs, mitigation strategies must be identified and documented in a Memorandum of Agreement (MOA) signed by the Applicant, SHPO, Lead Federal Agency, and the CPs.
DELIVERABLE(S): Permits/clear for construction.